## Backlog Tracker (PS Containers)
Backlog Tracker (PS Container Stories) |  |  |  | Work Identitifed Based on Grooming Till 08/04/2019. Below items are not included. 1. Does not include TwistLock Analysis. Work that may be required to fix the vulnerabilities. 2. Finishing work for containers (only partial covered here)
Rally # | Description | Plan Estimate | Assigned To | Functional Area | Must Have Category for 14.0 Per PM | Effort Type | Scrum Team View | Architects View | Comments
US555328 | [CloudNative][Helm]Verify Upgrading from container 14.0 to 14.1- Canary | 10 | 5-Dimensions | Support deployment with Helm Charts
US555334 | [CloudNative][Helm]Verify for Roll back- Blue Green | 10 | 5-Dimensions | Support deployment with Helm Charts
US555335 | [CloudNative][Helm]Verify for Roll back- Canary | 10 | 5-Dimensions | Support deployment with Helm Charts
US575429 | [Spike][CloudNative] Liveliness check of policy server can be improved by monitoring the PS state (instead of port) | 8 | 5-Dimensions | Monitoring | N | Dev | Y | N | (Architects) Requires Design change, Current design does not fit on prem and containers April 08 2019: (ScrumTeam) Improve accuracy w.r.t health monitoring of policy server in container (PM) Currently not in scope for 14.0 GA. can revisit if there are potential high risk scenarios or strong customer feedback around this. For now, a candidate for an enhancement .
US554559 | [POST PI4][CloudNative][PSM]Testing external admin store - Tier2 | 8 | 5-Dimensions | External administrator support | N | QA | Y | N | April 08 2019: (PM) Not a candidate for 14.0 GA, unless its blocking core customers who are validating it. Can defer into a later release and call out the stores that are not supported.
US554558 | [POST PI4][CloudNative][PSM]Support for all User stores as per present PSM - tier2 | 8 | 5-Dimensions | UD support | N | Dev | Y | N | (PM) will take it per customer demand but as we approach GA, we will close the window for certifying additional stores. Advertise on validate.ca.com the intended support matrix for 14.0.
US532920 | [POST PI-4][CloudNative]Config Retriever support for HTTP(git hub), Azure, GCE | 8 | 5-Dimensions | Additional Sources for Config Retriever | N |  | Y | N | (Architects) Not related to SSO specific functionality (PM) will get to it when we actually certify the cloud providers
US554553 | [POST PI-4][CloudNative][PSM]Support for all Session stores as per present PSM - tier2 | 8 | 5-Dimensions | Session Store Support | N |  | Y | N | (PM) will take it per customer demand but as we approach GA, we will close the window for certifying additional stores. Advertise on validate.ca.com the intended support matrix for 14.0.
US576651 | [POST PI4][cloudnative][PSMetrics]Research on other metrics suitable for ps autoscaling based on custom metrics | 8 | 5-Dimensions | Custom Metrics | N |  | Y | N | (Architects) This area may add lot of additional scope (PM) agree. candidate post customer feedback.
US532912 | [POST PI4][CloudNative][PSM]Support for all User Directories as per present PSM - Tier1 | 8 | 5-Dimensions | UD support | N | Dev | Y |  | (PM) will take it per customer demand but as we approach GA, we will close the window for certifying additional stores. Advertise on validate.ca.com the intended support matrix for 14.0.
US555453 | [CloudNative][Helm] Productize the helm POC work | 8 | 5-Dimensions | Support deployment with Helm Charts
US532929 | [CloudNative][Helm]Spike for Upgrading from container 14.0 to 14.1- Canary | 8 | 5-Dimensions | Support deployment with Helm Charts
US555456 | [CloudNative][Helm]Hooks development | 8 | 5-Dimensions | Support deployment with Helm Charts
US532900 | [POST PI4][CloudNative]Spike to introduce RBAC support for server components - [POST PI-4] | 8 | 5-Dimensions | RBAC | Y |  | Y | N | (Architects) Not related to SSO specific functionality (Daya) Document permissions needed for autoscaling, montioring. Sample Yaml files or guidelines. (Herb) Lets plan to do a parity check with the customers.
US532905 | [TBD][CloudNative]Testing RBAC support for server components - [POST PI-4] | 5 | 5-Dimensions | RBAC | N |  | Y | N | (Architects) Not related to SSO specific functionality (PM) Based on Customer Demand
US575281 | Cert8.db – Runtime Config Retriever cases | 4 | Wellspring | User Store Certificate Updates | Y |  | Y | N | (Architects) Onpar with Non Contaienr (Venu) Both Dev and Testing is required to support this usecase. (Daya) LDAP over ssl (connection to all stores)
US532904 | [POST PI4][CloudNative]Productize RBAC support for server components - Development - [POST PI-4] | 3 | 5-Dimensions | RBAC | N |  | Y | N | (Architects) Not related to SSO specific functionality (PM) Based on Customer Demand
US579457 | [CLoudNative][log-collector] Multiline log record support | 3 | 5-Dimensions | Logging | Y | Dev | Y | N | (Architects) Logging enhancement that can hold till 14.1 (Daya) actual single line is getting transled to multiline (Herb) Must Have to have clean data.
US532917 | [TBD][CloudNative]If we are supporting SSO with Java 11, we need to do necessary changes and test - [POST PI-4] |  | 5-Dimensions | Java Support | Y |  | Y | N | (Architects) Onpar with Non Contaienr (Herb) Long term support for Java to be based on Java 11. Reasonably high probability existing contract for Java might not extend beyond july? might need to consider openJDK, in the not so distant future. Might need to think again, if the size is large or other performance blockers.Try to groom to a good level of confidence, to get a better understanding of size. Recommended for 14.0.
US532909 | [CloudNative][PSM]Support for all policy stores as per present PSM - tier1 - [POST PI-4] | 15 | 5-Dimensions | Policy Store Support | Y |  | Y
US532928 | [TBD][CloudNative][Finishing work]Backward compatability with old agents(Webagent,ASA,ERP,SOA,sharepoint etc) | 13 | 5-Dimensions | Finishing Work | Y | QA | Y
US532910 | [CloudNative][PSM]Support for all Key stores as per present PSM - tier1 - [POST PI-4] | 13 | 5-Dimensions | Key Store Support | Y |  | Y
US532915 | [TBD][CloudNative]All External config files (while configuring any auth scheme or integration, etc.) that need to be copied to PS file system??? Do we need to ship those sample files or document on how customer can do it??? - [POST PI-4] | 13 | 5-Dimensions | TBD | Y | TBD | Y |  | (Jagan) APS.cfg, etc. (Herb) Avoid as much as possible, customers having to copy file from loc to another. At scale, this is going to get very difficult
US579128 | [CloudNative][Automation] Modification of tests related to PS Cache to work against containers | 10 | 5-Dimensions | Automation | Y |  | Y
US579091 | [POST PI4][CloudNative][AWS] verify IM/SM integrations | 8 | 5-Dimensions | AWS support | Y | QA | Y
US575272 | [POST PI4] Seperate secrets from values.yaml | 8 | 5-Dimensions | K8s Security | Y | Dev | Y
US532944 | [POST PI4][CloudNative][PSM]Testing external admin store - Tier1 | 8 | 5-Dimensions | External administrator support | Y | QA | Y
US555565 | [POST PI4][CloudNative]Finalize docker EE/CE and kubernetes versions and perform testing | 8 | 5-Dimensions | Certifying with latest release of K8s and Docker | Y | QA | Y
US555330 | [CloudNative][Helm]Spike for Roll back- Canary | 8 | 5-Dimensions | Support deployment with Helm Charts
US579130 | [CloudNative][Automation] Modification of tests related to Fail Over to work against containers | 8 | 5-Dimensions | Automation | Y |  | Y
US579086 | [POST PI4][CloudNative][AWS] Verify the ssl communication between the stores | 7 | 5-Dimensions | AWS support | Y | QA | Y
US532932 | [CloudNative][Finishing work]Benchmark Testing | 6 | 5-Dimensions | Finishing Work | Y | QA | Y
US577959 | [CloudNative][Finishing Work]Some policy server features to test as part of finishing work | 6 | 5-Dimensions | Finishing Work | Y | QA | Y
US579092 | [POST PI4][CloudNative][AWS] Verify RSA integration | 5 | 5-Dimensions | AWS support | Y | QA | Y
US555342 | [POST PI4][CloudNative][AuthSchemes] Kerberoes Auth scheme support in containers | 5 | 5-Dimensions | Authscheme support | Y | QA | Y
US574446 | [CLOUD NATIVE]SSL Communication should be enabled between policyserver and session stores for LDAP | 5 | 5-Dimensions | Session Store | Y | Dev | Y
US555325 | [CloudNative][Helm]Productize Upgrading from container 14.0 to 14.1- Canary | 8 | 5-Dimensions | Support deployment with Helm Charts
US532931 | [CloudNative][Finishing work]Endurance testing | 5 | 5-Dimensions | Finishing Work | Y | QA | Y
US532916 | [TBD][CloudNative]How is trouble shooting done for containers??? Installing external utilities, etc. - [POST PI-4] | 5 | 5-Dimensions | Troubleshooting | N | TBD | Y |  | (Dayakar) Externalizing Core dump is already taken care. Remote engineer part of another story.
US555332 | [CloudNative][Helm]Productize for Roll back- Canary | 8 | 5-Dimensions | Support deployment with Helm Charts
US579937 | [CloudNative]Fetching of session and audit store information from admin server | 5 | Wellspring | Session Store and Audit Store related | Y |  | Y
US579093 | [POST PI4][CloudNative][AWS] Verify APS functionality | 4 | 5-Dimensions | AWS support | Y | QA | Y
US499494 | [CloudNative][Finishing work]Verify Custom responses and Active expressions should support with containerized policy server | 4 | 5-Dimensions | Finishing Work | Y | QA | Y
US555458 | [CloudNative][Upgrade][Finishing work]Upgrading the server from 12.52 and 12.6 to 14.0 - Parallel upgrade- LDAP | 4 | 5-Dimensions | Finishing Work | Y | QA | Y
US532943 | [CloudNative][Finishing work]SDK testing with containerized policy server | 4 | 5-Dimensions | Finishing Work | Y | QA | Y
US579212 | Doc: Document Troubleshooting and Diagnostics information | 4 | 5-Dimensions | Content | Y |  | Y
US579869 | Video: Create a Video for a Basic Docker Deployment | 3.5 | 5-Dimensions | Content | Y | N/A | Y
US579220 | Video: Create a Video for Migrating from On-premise to Docker Deployment | 3.5 | 5-Dimensions | Content | Y | N/A | Y
US533101 | [CloudNative]Incorporating Customer Feedback from validation kits | 3 | 5-Dimensions | Customer Feedback | TBD | TBD | Y
US555340 | [post PI4][Continued] [CloudNative][AuthSchemes] OpenID Auth scheme support in containers | 3 | 5-Dimensions | Authscheme support | Y | QA | Y
US555872 | [POST PI4][CloudNative]Provide In memory tracing enable support | 3 | 5-Dimensions | Troubleshooting | Y |  | Y |  | (Jagan) smtrace events. Enable in registry?. provision to enable it from console.
US555329 | [CloudNative][Helm]Spike for Roll back- Blue Green | 6 | 5-Dimensions | Support deployment with Helm Charts
US576644 | [POST PI4][cloudNative][License]Create license.txt for containers and get approval from legal | 3 | 5-Dimensions | EULA | Y |  | Y
US555457 | [CloudNative][Upgrade][Finishing Work]Upgrading the server from 12.52 - 12.8 to 14.0 - with updating the schema - existing store - Rolling upgrade - Doc note (by taking clone of existing store) | 3 | 5-Dimensions | Finishing Work | Y | QA | Y
US554549 | [CloudNative][PSM]Support for all Audit stores as per present PSM - tier1 - [POST PI-4] | 3 | 5-Dimensions | Audit Store | Y |  | Y
US574019 | [Continued] [Continued] [CloudNative]SSL communication should be enabled between policy server and policy-store (LDAP) part 2 - [POST PI-4] | 3 | 5-Dimensions | SSL between Pserver and Pstore | Y |  | Y
US579582 | [CloudNative][GDP module]Limit Concurrent Login for CA Single Sign-On ( PWP Version: 3.2) | 3 | 5-Dimensions | GD Module | Y |  | Y |  | (Dayakar) via confi retriever is one of the ways. Certification story for GD module. (Siva) GD module certification can vary across modules. Need GD team to participate in certification. (Herb) Provide info to HCL team about the methodology that they should follow and make necessary code changes and certify. Shared responsibility. Full ownership is with HCL. Need to find out the business owner of the PWP modules and kickstart a project to certify. Connect them to Srinivas and Sudheer, to track.
US555323 | [CloudNative][Helm]Spike for Upgrading from container 14.0 to 14.1- Blue Green | 6 | 5-Dimensions | Support deployment with Helm Charts
US555338 | [CloudNative][POST PI4]Federation impact with containerized Policy server-OIDC | 2 | 5-Dimensions | Federation | Y |  | Y
US555337 | [CloudNative][Finishing work]Federation impact with containerized Policy server-SAML | 2 | 5-Dimensions | Federation | Y |  | Y
US555891 | [POST PI4][CloudNative]Twistlock scan for images | 2 | 5-Dimensions | Vulnerability Scanning | Y |  | Y
US532930 | [CloudNative][Finishing work]Lab Creation for Endurance and Performance tests | 2 | 5-Dimensions | Finishing Work | Y | QA | Y
US555460 | [CloudNative][Upgrade][Finishing Work]Verifying key store after the upgrade | 2 | 5-Dimensions | Finishing Work | Y | QA | Y
US555324 | [CloudNative][Helm]Productize Upgrading from container 14.0 to 14.1- Blue Green | 6 | 5-Dimensions | Support deployment with Helm Charts
US577956 | [CloudNative][finishing work]Testing agent discovery on containers | 2 | 5-Dimensions | Finishing Work | Y | QA | Y
US580216 | [Post PI 4] Once the containers were up and running change the master / super user password and see it updated successfully in all other components | 2 | 5-Dimensions | Operational | Y |  | Y
US581327 | Support in-place upgrades for server side components (SP updates) |  | 5-Dimensions | Upgrade (Service Pack) | Y | Dev | Y |  | PS, Admin PS image or both images - SP updates to be tested. Consider both schema changes and no updates to schema as well, for these scenarios. Rollback (if there are any schema changes, rollback may not be possible. workaround is to use cloned stores and incase of the need to upgrade, point to the original store. need to test this usecase as well). Canary should be taken up, post the regular rolling update. what happens if customer needs to touch only a subset of policy servers? is this still applicable in container type deployments? it is complex to support such scenarios. might not be a good idea.
US577951 | [CloudNative]IWA authscheme testing on containers |  | 5-Dimensions | Authscheme support | Y | QA | Y |  | AG on on-prem windows and ps on container
US575285 | [CloudNative][Automation]Run APS, RSA Smoke and PS WA Regression template on containers harness |  | 5-Dimensions | Automation | Y | Dev | Y
US577950 | [CloudNative][finishing work]On-premise 14.0 feature testing on containers |  | 5-Dimensions | Finishing Work | Y | QA | Y
US577961 | [POST PI4][CloudNative]Handling Custom made registry changes on containers |  | 5-Dimensions | Registry Changes | TBD |  | Y |  | (Dayakar) PCO ? challenges might exist when the registry files are not update. (Venky) new registry keys as a fix during patches - might necissitate (Mukesh) base framework for PCO exists. testing effort will be high. rough estimate might be close to 60-70 points. (Jagan) smreg is a multiwrite. assumption of using config retriever is correct. Need to test this with a config retriever.(Story needed) Current default settings for connections needs to change.
US555331 | [CloudNative][Helm]Productize for Roll back- Blue Green | 6 | 5-Dimensions | Support deployment with Helm Charts
US579131 | [CloudNative][Automation] Modification of tests related to OVM to work against containers |  | 5-Dimensions | Automation | Y |  | Y
US579133 | [CloudNative][Automation] Modification of tests related to PS_WA_Regression to work against containers |  | 5-Dimensions | Automation | Y |  | Y
US561514 | [Post PI4]Use Alpine OS for Metrics Exporter | 5 | 5-Dimensions | Container OS | N |  | Y | N | (Architects) Not much of added advantage to fulfil this in 14.0 (Saurabh) Image Size is quite large. (Dayakar) Given that this is for metrics exporter, CentOS should be fine. Its just a matter of ~100MB more space
US555869 | [POST PI4][Continued] [CloudNative]Verify APM Integration with containers | 5 | 5-Dimensions | APM Integration (with prometheus support) | N | QA | Y |  | (Herb) APM v11.5?. Connect with APM team, to see if their plan to integrate with Promtheus for CA SSO metrics., is on track etc.
US499492 | [POST PI-4][CloudNative]Remote Engineer service should be available/run in containers | 5 | 5-Dimensions | Remote Engineer | N |  | Y |  | (Herb) waiting for feedback from Support team on the path forward. Leave it off from manifest work for release.
US555454 | [CloudNative][Helm]Test SSO install package deployed by helm | 5 | 5-Dimensions | Support deployment with Helm Charts
US555326 | [CloudNative][Helm]Verify Upgrading from container 14.0 to 14.1- Blue Green- ODBC | 5 | 5-Dimensions | Support deployment with Helm Charts
US555742 | [CloudNative][Helm]Verify Upgrading from container 14.0 to 14.1- Blue Green - LDAP | 5 | 5-Dimensions | Support deployment with Helm Charts
US532918 | [POST PI-4][CloudNative]Policy Server and Admin UI images size reduction? | 3 | 5-Dimensions | Container OS Optimization | Y |  | Y | Y | (Architects) Not much of added advantage to fulfil this in 14.0 (Dayakar) Purpose built images for worker PS (remove extra tools).
US575430 | [Observations] It is observed that Policy server (worker PS) is taking considerable time to spin-up. Can we optimize it? | 3 | 5-Dimensions | Performance | N |  | Y |  | (Mukesh) this is already taken care of. (Dayakar) Estore as a container is something can be considered. (Herb) Spike to deploy CA Directory as a container. (Venky) Testing stories need to be planned, to understand the gaps
US579790 | [CloudNative][Automation] Template creation for FailOver, cache and OVM | 3 | 5-Dimensions | Automation |  |  | Y
US532911 | [CloudNative][PSM]Support for all Session stores as per present PSM - tier1 - [POST PI-4] | 2 | 5-Dimensions | Session Store Support | N |  | Y |  | (PM) will take it per customer demand but as we approach GA, we will close the window for certifying additional stores. Advertise on validate.ca.com the intended support matrix for 14.0.
US555573 | [CloudNative][Helm] Identify helm packaging format | 1 | 5-Dimensions | Support deployment with Helm Charts
US554551 | [CloudNative][PSM]Support for all policy stores as per present PSM - tier2 - [POST PI-4] |  | 5-Dimensions | Policy Store Support | N |  | Y | N | (PM) will take it per customer demand but as we approach GA, we will close the window for certifying additional stores. Advertise on validate.ca.com the intended support matrix for 14.0.
US554550 | [CloudNative][PSM]Support for all Key stores as per present PSM - tier2 - [POST PI-4] |  | 5-Dimensions | Key Store Support | N |  | Y | N | (PM) will take it per customer demand but as we approach GA, we will close the window for certifying additional stores. Advertise on validate.ca.com the intended support matrix for 14.0.
US554556 | [CloudNative][PSM]Support for all Audit stores as per present PSM - tier2 - [POST PI-4] |  | 5-Dimensions | Audit Store | N |  | Y | N | (PM) will take it per customer demand but as we approach GA, we will close the window for certifying additional stores. Advertise on validate.ca.com the intended support matrix for 14.0.
US532914 | [TBD][CloudNative]FIPS migrations support??? - [POST PI-4] |  | 5-Dimensions | FIPS Migration | N |  | Y | N | (Architects) Customer base may be too low (Herb) Rev 1. Migration need not be supported.
US577964 | [POST PI4][CloudNative]Tesla Integration testing on containers |  | 5-Dimensions | ? | N |  | Y | N | (Architects) Customer base may be too low (PM) Not needed as Identity Service is EOLed
US577963 | [POST PI4][CloudNative] Fail over/LB of all Stores |  | 5-Dimensions | Policy Store Redundancy | Y |  | Y |  | (Dayakar) Mostly testing but for ODBC store, config files are set correctly. LDAP Policy Store HA - configuration done by config retriever. Samples of key configuration in templates should be provided.
US575260 | [After PI-4] Productize Secret Managment using hashicorp vault | 13 | 5-Dimensions | External administrator support | TBD | Dev | Y | N | (Venky) need to explore different ways of integration. environmental variables mode approach?
US575269 | [POST PI4] Vet the k8s deployment with podsecurity policies | 8 | 5-Dimensions | K8s Security | Y | QA | Y | N | (Dayakar) Certify deployment with K8s hardening (config maps, secrets, types of volumes). previleged operations within the sso pods constructs can become blockers for deployment. both dev and testing effort. (Herb) Lets get commentary from customers and also understand from the design perspective to see how we can address it. its going to be important.
US575259 | [Spike][CloudNative] - POC on Secret Management using Hashicorp vault | 8 | 5-Dimensions | K8s Security | Y |  | Y | Y
US499469 | [POST PI4][CloudNative]Externalize derby db with verification | 8 | 5-Dimensions | External administrator support | Y | Dev | Y | Y
US532933 | [CloudNative][Finishing Work]Internationalization and localization testing of container PS | 5 | 5-Dimensions | Finishing Work | Y | QA | Y | N | (siva) i18n character testing. yaml files only english. some scenarios. e.g DSN names,
US575282 | [POST PI4]identifying the boundaries for the parameters / values in values.yaml | 6 | 5-Dimensions | Constraints Testing | Y |  | Y | N | (Dayakar) e.g DSN max length, namespace. finishing work candidate
US499470 | [POST PI4][CloudNative]External Administrator Authentication for AdminUI should be configured in containers | 2 | 5-Dimensions | External administrator support | Y | Dev | Y | Y | (PM): 10/04/2019 Prevalence of external administrator is high and hence falls under a "must have" category. Customers more often use LDAP. Lets surface the dependency on IAM FWK and work with the broader engineering team to see how that can be solved. (Eng) 10/04/2019 Derby DB dependency. Challenges exist that needs to be solved.
US545872 | [POST PI4]Test SessionAffinity once DerbyDb is externalized | 2 | 5-Dimensions | External administrator support | Y | QA | Y | Y
US561521 | [POST PI4]Admin UI accessibility using HTTPS with latest Ingress Controller | 4 | 5-Dimensions | K8s Ingress Controller | Y | Dev | Y | N | 10/04 (Herb) frequency of ingress controller? at the time of GA, we freeze the certification to a particular version. 6months might work but not anything older. Hold the decision till PI5. (Venky) Draw a timeline after which we do not engage. (Madhu) Need to fix with current "latest" . May be too outdated before GA. (Siva) updates 6 weeks interval
US575263 | [POST PI4]Research the feasibility of using PVC and PV | 4 | 5-Dimensions | K8s Security | N |  | Y | N | (Dayakar) allocate quota.